## Slide 1: Change portfolio status — overall AMBER: core migration and card collections need decisions this month
Status as of 2 October 2026 · Weekly portfolio review · Prepared for: Head of Consumer Banking · Owner: PMO
WORKSTREAM | STATUS | THIS PERIOD | NEXT PERIOD | OWNER
Digital onboarding 2.0 | ● On track | Release 3 live in two states; funnel conversion +4 pts | National rollout 20 Oct; marketing launch | J. Alvarez
Core deposits migration | ● At risk | Dress rehearsal 2 slipped one week on reconciliation defects | Go / no-go for 14 Nov cutover due 24 Oct | M. Chen
Card collections uplift | ● Off track | Dialer vendor contract unsigned; hiring 40% complete | Decision on interim outsourcing needed | S. Patel
Branch network optimisation | ● On track | 6 of 14 consolidations done; attrition 1.8% vs 3% tolerance | Next four closures 1 Nov; staff redeployment | R. Okafor
Open banking APIs | ● At risk | Security review raised 3 high findings; 2 closed | Close final finding by 10 Oct; certification test | L. Novak
Complaints handling redesign | ● On track | Average resolution 6.1 days (target 7) | Automate acknowledgement letters | A. Rossi
OVERALL STATUS
● AMBER
3 on track · 2 at risk · 1 off track
DECISIONS NEEDED
Approve interim outsourcing of early-stage collections
S. Patel · by 10 Oct
Confirm 14 Nov cutover or defer migration to January
M. Chen · by 24 Oct
● On track: on plan ● At risk: slippage with mitigation in place ● Off track: off plan, decision needed
Notes: RAG status tracker. One row per workstream: status, what happened this period, what happens next, owner. Status always carries a word next to the colour. Overall rating and the escalations that need the reader's decision sit on the right so they are not buried in the table.