## Slide 1: Weekly update — Consumer Banking analytics — week ending 2 October 2026
For: Head of Consumer Banking · Team: Data & Analytics, 12 FTE, 2 open roles · Overall health: Green · Next 1:1: 8 October
DONE THIS WEEK
September deposit MI published on day 3
Two days faster than August; commentary automated.
Finance MI · 3 Oct
Card vintage delinquency deep-dive delivered
2024 vintage isolated as the driver; shared with Risk.
Credit analytics · 1 Oct
Data reconciliation suite v2 in production
Row and column checks live for 25 source-target pairs.
Platform · 30 Sep
IN PROGRESS
HYS repricing impact model
Attrition scenarios for −15 and −25 bps; draft Tuesday.
Pricing analytics · 70% done
Branch consolidation dashboard
Adding complaint and attrition tiles per market.
Distribution MI · 50% done
NEXT WEEK
Q3 business review pack
Numbers locked Wednesday; narrative review Thursday.
Due 10 Oct
Collections dialer data-feed design
Depends on the vendor contract (see blockers).
Starts 7 Oct
BLOCKERS AND ASKS
Collections dialer contract still unsigned
Blocks the data-feed design; Procurement escalation needed.
Ask: call the Procurement lead
Two analyst roles open for 9 weeks
Risk analytics backfill; contractor cover proposed to December.
Ask: approve contractor to Dec
Notes: Weekly update board (dark). Four columns: done, in progress, next, blockers and asks. Every card is a headline plus one line of detail plus an owner or date. The blockers column is the reason the reader opens the slide, so each blocker ends with a specific ask.