## Slide 1: 2027 roadmap: five initiatives and three decision gates before March — core migration is the critical path
Consumer Banking change roadmap, Q4 2026 – Q3 2027 · Quarterly planning review · Owner: PMO · Status as of October 2026
Q4 2026
Q1 2027
Q2 2027
Q3 2027
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Core deposits migration
M. Chen · critical path
Go / no-go 24 Oct
Cutover 14 Nov
Digital onboarding 2.0 — national rollout
J. Alvarez
National launch 20 Oct
Card collections uplift
S. Patel
Outsourcing decision 10 Nov
Dialer live Feb
Branch network phase 2
R. Okafor · pending approval
Approval gate Jan
Open banking APIs
L. Novak
Certification Dec
Premium APIs (tentative)
Today
Committed delivery
Pending approval
Decision gate
Milestone
Notes: Roadmap (Gantt). One row per initiative with owner; bars are delivery windows, diamonds are the decisions the reader owns, circles are milestones, and the dashed line is today. Pending work is drawn in the lighter colour so nobody reads it as committed.