## Slide 1: Proposal: automate early-stage card collections outreach — $4.8m investment, 19-month payback, $6.1m NPV
Business case one-pager · Investment Committee pre-read · Sponsor: Head of Consumer Banking · Decision requested: Phase 1 funding by 31 October
Investment
$4.8m
over 12 months
Run-rate benefit
$5.5m p.a.
from month 13
Payback
19 months
from project start
3-year NPV
$6.1m
at a 9% hurdle rate
Chart: Cumulative net cash flow, $m — break-even in Q7
| Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
Cumulative net cash flow | -1.6 | -3 | -3.4 | -3.1 | -1.7 | -0.4 | 1 | 2.4 | 3.8 | 5.2 | 6.5 | 7.9
BENEFITS ($5.5M RUN-RATE)
Lower roll-to-loss: −10 bps charge-off rate on the $6.2bn card book — $3.1m
Collector productivity +22% through automated early contact — $1.6m
Fewer complaints and manual letters — $0.8m
KEY ASSUMPTIONS
Contact rate rises from 31% to 48% (vendor benchmark 52%)
No change to regulatory contact-frequency limits
RISKS AND MITIGATIONS
Vendor delivery slip → contractual penalties and a phased go-live
Fairness → Compliance-approved scripts and a pre-launch conduct review
Decision requested: approve Phase 1 funding of $1.9m (design and vendor selection) by 31 October; Phase 2 is subject to pilot results in February.
Notes: Business case one-pager. Four headline numbers a committee asks for first, a cumulative cash-flow chart that shows break-even, then benefits with their arithmetic, the assumptions the case depends on, the risks with mitigations, and the precise decision requested.